## Main
Scrum Project
Product | 201-file upload by employee |  | Product Status | For Development
Active versions |  |  | Sponsor
Team
Scrum Master | Timothy Ckhille Velasco |  | Product Owner | Timothy Ckhille Velasco
Developers | Keith Topino |  | Project Champion
| Louie Cortero |  | Other Stakeholders | Manuel Seabastian (Proctor)
| Maria Theresa Urquiza |  |  | Jojo Castillo (Adviser)
Jell Ellema
Joshua Magno
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Meeting | Dec 27, 2021 | Dec 27, 2021 | Done |  | Spr. 1.1 | 2021-12-27 | 2021-12-27 | complete | 22 | 22
2 | start of coding | Jan 2, 2022 | present | In Progress |  | Spr. 1.2 | 2022-01-02 | ongoing | incomplete | 22 | 20
3 | Complete and working version | 2021-12-23 | 2022-02-27 | In Progress |  | Spr.1.3

## Backlog
Backlog
Id | Theme | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
DM-1 | opportunity | Team | Mandatory Meeting | assigning of task to each members |  |  | high | completed
DM-2 | opportunity | Team | Start of Coding | we can start |  |  | high | in progress
DM-3 | opportunity | Team | Complete and working version | we can present our project on time |  |  | hign | in progress

## Tracker
Sprint Tracker
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Pending | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 | 221 | Meeting |  | complete | 8 | 2 | 6 | 1 |  | 1
2.1 | 224 | start of coding |  | in progress | 2 | 1 | 1 |  | 1
2.2 | 225 | paper revisions |  | in progress | 5 | 5 | 0 |  | 1 |  | 2 |  | 1 | 1
3.1 | 229 | Major Revisions and Coding |  | in progress | 3 | 3 | 0 |  |  | 1 |  | 1 |  |  | 1
3.2 | 251 | Final Revisions and Testing |  | in progress | 13 | 13 | 0 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
[6 empty] | 1 | -1 | [9 empty] | 1
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
|  |  |  | Total | 31 | 25 | 6 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 2
|  |  |  | Burn down |  |  |  | 27 | 23 | 20 | 17 | 15 | 13 | 11 | 9 | 8 | 6
|  |  |  | Burn up |  |  |  | 4 | 8 | 11 | 14 | 16 | 18 | 20 | 22 | 23 | 25

## Impediment
Impediments
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On | Remarks

## Retrospective
Retrospective Log
Sprint # | Date | Owner | Continue Doing | Start Doing | Stop Doing | Remarks

## Summary
Reports & Dashboards
Sprint Velocity
Burn down Chart | Burn up Chart

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms